## Project schedule
| Gantt Chart – Project Timeline for Web-Based IT Supervisor Portfolio | [6 empty] | Project start: | [7 empty] | 2025-05-26
[8 empty] | Display week: | [7 empty] | 1
[8 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-22 | [6 empty] | 2025-06-29 | [6 empty] | 2025-07-06 | [6 empty] | 2025-07-13
| TASK | PROGRESS | START | END | DURATION (Days) | Progress Status | time axis 2025-05-26 to 2025-07-19
 | time axis 2025-05-26 to 2025-07-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Milestone 1 – Communication & Coaching
| Define Project Scope & Website Sections | 100% | 2025-05-26 | 2025-05-30 | 5 | Accomplished | 5
| Draft Executive Proposal Content | 100% | 2025-05-31 | 2025-06-03 | 4 | Accomplished | 4
| Design “About Me” and Branding Layout | 100% | 2025-06-04 | 2025-06-09 | 6 | Accomplished | 6
| Develop Coaching Toolkit | 100% | 2025-06-10 | 2025-06-13 | 4 | Accomplished
| Build Team Communication Page | 100% | 2025-06-14 | 2025-06-18 | 5 | Accomplished | 5
| Link Tools with Live Navigation | 100% | 2025-06-19 | 2025-06-20 | 2 | Accomplished | 2
Milestone 2 – KPIs, Budget & Leadership
| Research KPI Templates & Budget Formats | 100% | 2025-06-21 | 2025-06-24 | 4 | Accomplished | 4
| Develop KPI Dashboard Interface | 100% | 2025-06-25 | 2025-06-26 | 2 | Accomplished | 2
| Design Budget Management Spreadsheet | 100% | 2025-06-27 | 2025-06-30 | 4 | Accomplished | 4
| Create Team Leadership Toolkit Page | 100% | 2025-07-01 | 2025-07-02 | 2 | Accomplished | 2
| Integrate HR Templates for Team Supervision | 100% | 2025-07-03 | 2025-07-05 | 3 | Accomplished
| Link Performance Tools to Navigation | 100% | 2025-07-06 | 2025-07-06 | 1 | Accomplished | 1
Milestone 3 – Ethics, Culture & Final Integration
| Draft Ethics & Inclusion Content | 0% | 2025-07-07 | 2025-07-09 | 3 | Not started | 3
| Build Ethics & Inclusion Webpage | 0% | 2025-07-10 | 2025-07-11 | 2 | Not started
| Design Client Support Manual Page | 0% | 2025-07-12 | 2025-07-14 | 3 | Not started | 3
| Develop Final Website Design/Layout Enhancements | 0% | 2025-07-15 | 2025-07-16 | 2 | Not started | 2
| Create Final Video Presentation for Website | 0% | 2025-07-17 | 2025-07-18 | 2 | Not started | 2
| Conduct Final Testing & Publish Full Portfolio | 0% | 2025-07-19 | 2025-07-21 | 3 | Not started | 3
APA Citation
Sunny, M. N. M., Sakil, M. B. H., & Al, A. (2024). Project management and visualization techniques a details study. Project Management, 13(5), 28-44.
Note. Adapted from Sunny, Sakil, and Al (2024).